## Sheet1
REGISTER
Document Name: Drawing Issue Register |  |  | Revision 2,04
Document Number: CRD-MSP-005REG |  |  | Page 1 of 1
Effective Date: 05 August 20019
Approved by:
DRAWING ISSUE REGISTER
Project: | Burgersfort Bulk Sewer Pumpstation
Project no. | 1121
Discipline: | ELECTRICAL |  | 001 | 002 | 003 | 004 | 005 | 006 | 007 | 008 | 009 | 010 | 011 | 012 | 013 | 014 | 015 | 016 | 017 | 018 | 019 | 020 | 021 | 022 | 023 | 024 | 025 | 026 | 027 | 028 | 029 | 030 | 031 | 032 | 033 | 034 | 035 | 036 | 037 | 038 | 039
|  |  | 2023/03/30 | 18/09/2023
Drawing number | Drawing Title | Size
NT06-22-1121-400-001 | BUILDING LIGHTING LAYOUT | A1 | bar: 001 to 002
NT06-22-1121-400-002 | SITE LIGHTING LAYOUT | A1 | bar: 001 to 002
NT06-22-1121-401-001 | BUILDING SMALL POWER LAYOUT | A1 | bar: 001 to 002
NT06-22-1121-402-001 | KIOSK SINGLE LINE DIAGRAME | A1 | bar: 001 to 002
NT06-22-1121-402-002 | DISTRIBUTION BOARD-A LAYOUT | A1 | bar: 001 to 002
NT06-22-1121-402-003 | DISTRIBUTION BOARD-A SIMULATIONS LAYOUT | A1 | bar: 001 to 002
NT06-22-1121-426-001 | SITE SLEEVE LAYOUT | A1 | bar: 001 to 002
Issued for:
E: Electronic (e-mail/CD) | Information
P: Paper | Approval | bar: 002
Tender
Costruction
As-built
Distribution | Attention
CLIENT
ARCHITECT
QS
MAIN CONTRACTOR |  |  | 002: 3
PLEASE SPECIFY:
Project Stage | Project Rev Codes
Status Quo | A1
Feasibility Study | B1
Inception | C1
Preliminary | D1
Detail Design | E1
Issue for Tender | F1
Issue for Construction | 0
As Built | AB
TOTAL ISSUED DRAWINGS A1 SHEETS |  |  | 002: 7
Issued by (on behalf of AMCE) |  | RECEIVED BY
DATE |  | DATE